## Slide 1: Our Mission
State what you believe is the primary mission

## Slide 2: Kwazulu-Natal Diving Overall Aim
To ensure that we promote competitive diving from beginners through to national level throughout the province

## Slide 3: DIVING: Objectives
To implement competitive diving programmes in at two Districts in the 2022-2023 period
To strengthen the junior fast tracking programme
To ensure participation at the national championships and in national squads

## Slide 4
Objective | Key Activities
To implement competitive diving programmes in two Districts | Chairs of two districts indicate their commitment to developing diving in their districts. Identification and training of District Diving Co-ordinators Identification of facilities Invitation to clubs and schools to forward names of athletes Implementation of beginners diving programme
To strengthen the junior fast tracking programme | Selection of athletes from beginners programmes Bi-weekly training sessions Participation in provincial and national age group competitions
To ensure participation at the national championships and in national squads | Establish a diving high performance unit Identification of coach and assistant coach Selection of athletes from Junior Fast Tracking Programme Participation in monthly district level competitions Selection of team for SSA Nationals Identification of top performance athletes for advanced training, scientific assessments and monitoring
Activities

## Slide 5
Objective | Key Activities | Outputs and Smart Targets | Resources Required to complete Activities
To implement competitive diving programmes in two Districts | Chairs of two districts indicate their commitment to developing diving in their districts. Identification and training of District Diving Co-ordinators Identification of facilities Invitation to clubs and schools to forward names of athletes Implementation of beginners diving programme | Two districts with programmes by 30 April 2023 | Project Manager: Kim Capital Costs: Trampoline – R20,000 Operating Costs: Coaching Stipend – R5000 per month x 12 months – R60,000
To strengthen the junior fast tracking programme | Selection of athletes from beginners programmes Bi-weekly training sessions Participation in provincial and national age group competitions | Criteria for squad finalised by 30 June 2022 Squad identified by 31 July 2022 100 % of squad attend Provincial Competition 70% of squad attend National competition | Project Manager: Capital Costs Operating Costs – Travel costs for athletes – R20,000
To ensure participation at the national championships and in national squads | Establish a diving high performance unit Identification of coach and assistant coach Selection of athletes from Junior Fast Tracking Programme Participation in monthly district level competitions Selection of team for SSA Nationals – March 2023 Identification of top performance athletes for advanced training, scientific assessments and monitoring | High Performance Plan prepared for 4 year period by 31 July 2022 Coach and Assistant coach criteria prepared by 30 June 2022 Coach and Asst Coach identified by 31 March 2023 HP Athletes identified by 31 August 2022 | Project Manager: Capital Costs Operating Costs Pool hire – R5000 per year, National travel support – R20,000,
Activities and Budget Estimates

## Slide 6
KZN Diving Board:
Challenges and Threats
Shortage of coaches in the Province
Lack of facilities with diving boards
Shortage of judges
Parent involvement for the development divers
Cost of transport for development divers to training and competitions
Funding
  Fundraisers, corporate sponsorships (tax certificates?)